Eastern Partnership facility

Regional platform for domestic election observation initiatives

Plan of activities for 2011

August

- Identification of independent expert to write the observation methodology in conjunction with NGOs

September

- Assessment of best practices of domestic election observation in Eastern Partnership countries and inquiry on training needs, Moldova, Belarus, Ukraine

October

- Informal meeting with head of PACE election observation missions, Strasbourg 3. - 6.10.

- Review of existing standards and principles for domestic election observation (drafting of part I of handbook)

- Assessment of best practices of domestic election observation in Eastern Partnership countries and inquiry on training needs, Armenia, Azerbaijan, Georgia (drafting of part II of handbook)

November

- Working meeting with NGOs regarding the joint observation methodology (place and date tbc)

- Creation of a joint observation methodology (drafting of handbook part III)

- Dissemination of draft handbook including standards, a code of conduct, best practices and a methodology for domestic election observation to NGOs for review

December

- Discussion of the draft handbook by NGO experts. PACE, ODIHR and EU observer secretariat staff shall be invited as well – Strasbourg 6.12.2011. (tbc)

- Planning of 2012 activities – NGO representatives & CoE – Strasbourg 7.12.2011 (tbc)

January 2012

- Publication of handbook

- Meeting with heads of PACE election observation missions, OSCE/ODIHR representatives and EU observers – NGO representatives, CoE – Strasbourg 16.-20.1. (tbc)

- Training of trainers on new election observation methodology – expert, NGOs – Strasbourg 16.-20.1. (tbc)